## Task Management
GROUP 04 | Project - SHOE SHOP
Reference Layout Link: https://similux-jewelry.myshopify.com/
Deploy Link: https://bcs-07-capstone-2-g4-shoe-shop.vercel.app/
Youtube Demo: https://youtu.be/A0MIL6UZaCA
Team member
1 | Huỳnh Quang Bảo
2 | Nguyễn Đình Anh Hào
Tasks Name | Sub tasks | API | Start Date | Finish Date | % Completion | Assigned Member | Notes
Setup and Self-research | 05/06/2023 - 08/06/2023
Global
| Header | None | 2023-06-10 | 2023-06-10 | 90% | Huỳnh Quang Bảo | Fixed numbers for liked shoes and shopping cart
| Footer | None | 2023-06-15 | 2023-06-15 | 100% | Huỳnh Quang Bảo
| Back to Top | None | 2023-06-15 | 2023-06-15 | `100% | Huỳnh Quang Bảo
HOME
| Navbar | None | 2023-06-11 | 2023-06-11 | 95% | Huỳnh Quang Bảo | Have not handle the search action in the navbar
| Carousel | None | 2023-06-11 | 2023-06-11 | 100% | Huỳnh Quang Bảo
| Deals | None | 2023-06-12 | 2023-06-12 | 100% | Huỳnh Quang Bảo
| Flash Sales | None | 2023-06-12 | 2023-06-12 | 100% | Huỳnh Quang Bảo
| Trending | None | 2023-06-13 | 2023-06-13 | 100% | Huỳnh Quang Bảo
| Products | getProduct getProductByCategory | 2023-06-13 | 2023-06-13 | 90% | Huỳnh Quang Bảo | Have not set the "Quick Add" button for products
| Customers | None | 2023-06-14 | 2023-06-14 | 100% | Huỳnh Quang Bảo
| Services | None | 2023-06-14 | 2023-06-14 | 100% | Huỳnh Quang Bảo
DETAIL
| Details | getById | 2023-06-12 | 2023-06-13 | 100% | Nguyễn Đình Anh Hào
| Services | None | 2023-06-14 | 2023-06-14 | 100% | Nguyễn Đình Anh Hào
| Customer Reviews | None | 2023-06-14 | 2023-06-15 | 100% | Nguyễn Đình Anh Hào
| Related Products | getById | 2023-06-15 | 2023-06-15 | 90% | Nguyễn Đình Anh Hào | Responsive is still broken in some screens
| Collections | None | 2023-06-16 | 2023-06-16 | 90% | Nguyễn Đình Anh Hào | Responsive is still broken in some screens
REGISTER
| Register | signUp | 2023-06-15 | 2023-06-16 | 95% | Huỳnh Quang Bảo | Not finish: check the checkbox inputs and disable the create button in the case that the customer have not check them yet